## Implementation Plan
Inter-Departmental Draft Action Plan
Project Purpose: The overall project purpose is to support the implementation of the recommendations from the 'Still Waiting' report which provided outlined the results of a review of mental health services and support for children and young people in Northern Ireland.
Updated: November 2021 V7
1. Key Theme: Working Effectively and Collaboratively
Ref ID | Recommendation | Link to Rec | Action | Completion Date | Lead | Key Partners | Status | Comments
Objective: Clear governance structures for development of CAMHS
1.1 | NICCY recommends the establishment of a high level multi-agency, multisectoral project board that is tasked with the development of a comprehensive, adequately resourced action plan for taking these recommendations forward. | 1 (c) | Establish an Inter-Departmental Project Board with cross sectoral representation to develop and implement an action plan in response to the NICCY Still Waiting Report recommendations. | 2021-06-01 | DoH | Project Board | Complete | The project board has been established and is due to meet every 2 months to review progress. The board was suspended for 6 months in 2020 due to Covid. | The IDG has shown itself to be a very effective mechanisim at bringing a mulit-agency and multi-sectoral focus to the issues rasied in Still Waiting. The efforts taken to review the Action Plan during this year to make it SMARTer is welcomed.
1.2 | As Above | 1 (c) | Finalise and sign off on the Still Waiting Action Plan, to include engagement with children and young people. | 2021-11-30 | DoH | Project Board | In progress | Draft action plan being refreshed. Consultation with children and young people took place on 5 October 2021. Finalised SWAP to be presented to the Minister for sign off. | The IDG recognises the importance of engaging with CYP on mental health policy and service planning- to do this in a meaningful way, child and young person accessible information is needed and a mechanism developed to build capacity and facilitate engagement on an ongoing basis.
Objective: Sustainable investment in CAMHS
1.3 | The use of the fund mapping methodology and analyses of need, to map increases in spending on emotional and mental health services over time, and to demonstrate how additional resources are being effectively and efficiently allocated to meet the needs of children and young people; | 1 (b) | Create a fund map of spending in children and adolescent mental health and emotional wellbeing services. | This action will be taken forward as part of the Mental Health Strategy 2021-2031 | DoH | DoH | In progress | This action is being taken forward as part of the 2021-31 Mental Health Strategy and associated Funding Plan. The strategy and funding plan were published by DoH in June 2021. | The publication of an investment plan alongside the mental health strategy was very welcome, as it provided greater clarity on the investment required to fill the current gaps. However, the increase in CAMHS funding to 10% of adult funding outlined in the MHS is not based on an assessment of need of the NI CYP population. A more detailed fund mapping exercise is required to fully understand the gap between current investment and what is needed to ensure CYP have access to a comprehensive range of mental health services.
1.4 | The development of a Children and Young People’s Mental Health Transformation Fund to drive the change required. This should be a long term and sustainable ‘funding and practice partnership model’, which takes account of the investment required across all key services and sectors included in the Stepped Care Model; | 1 (a) | Increase funding for CAMHS service. | This action will be taken forward as part of the Mental Health Strategy 2021-2031 | DoH | DoH | In progress | This action is being taken forward as part of the 2021-31 Mental Health Strategy. Action 10 of the strategy is "To increase the funding for CAMHS to 10% of adult mental health funding". | As above- 1.3 We would emphaisis that funding required for services goes beyond statutory services and should be based on a long term and sustainable ‘funding and practice partnership model’, which takes account of the investment required across all key services and sectors included in the Stepped Care Model and which includes the Voluntary and Community / Youth Sector.
Objective: Collect better information more regularly | [11 empty] | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS | Objective: Clear governance structures for development of CAMHS
1.5 | The CAMHS Dataset should be fully implemented across each HSCT. Adequate resources should be provided to establish and maintain the system. Data should be published on a regular basis, in line with other health statistical reporting. The Dataset should be augmented to include additional basic information and data, required to monitor services and effectively plan CAMHS. | 47 | Full implementation of CAMHS dataset. |  | HSCB | DoH | Complete | A full CAMHS dataset is in place. HSCB has met with the Encompass Director to ensure the CAMHS dataset will be captured by the new system when it is implemented across Trusts from January 2023. DoH are scoping options for sharing information captured by the CAMHS dataset in the public domain. | We recognise the importance of the CAMHS Dataset for information management purposes. Standardised regional information is essential for governance, commissioning and operational decision making. For this reason we would like to see the dataset augmented to include the types of data referenced in NCCYs Still Waiting report. It is also vital that CAMHS data is published for public use and recognised as a pubic asset. The Office for Statistics Regulation carried out a review of mental health statistics in NI in 2021 in which it recommended improvements in the accessiblity and quality of such data.
1.6 | The DoH should develop a universal health information system linked to every individual child, to inform every health professional coming into contact with a child and/or their parents/carers. This should link to other information systems, such as UNOCINI. ‘Patient level’ data should be integrated into statistical reports as part of a transparent and accountable information reporting system, so that the impact of services on outcomes for children and young people can be tracked. | 45 | Development of Encompass across the HSCT to provide a system of recording and reporting on patient data and trends. | Ongoing | Encompass | DoH | In progress | The developement of Encompass is being taken forward across HSC. Going forward the Mental Health Strategy will provide an alternative solution for implementation of this action. Action 34 of the Strategy is to "Develop a regional Outcomes Framework in collaboration with service users and professionals, to underpin and drive service development and delivery". A Regional Outcomes Framework Steering Group has been established to oversee and direct this work. The first Steering Group meeting is scheduled to take place in December. | It is vital that a range of child health data users are involved in the process of considering the functionality required for a new information management system. NICCY made this point in the context of the whole health and social care system in its recent Child Health Waiting List Review- More Than A Number. With respect to measuring outcomes, it is vital that children and young people are consulted on measures to ensure that they have meaning and hold importance to children and young people.
1.7 | Government should ensure that the first Northern Ireland Prevalence Survey of children and young people’s mental health is completed by year end 2019/20, and published soon thereafter. Further prevalence surveys should be repeated every 3–5 years. | 46 | Development of prevalence study into children’s and adolescent’s mental health. | 2020-10-01 | HSBC |  | Complete | A Data Analyst has been employed by Ulster University for 15 months to maximise the potential of the dataset and to produce 6 high level papers. | Welcome the resource provided to further mine data collected from the prevalance survey. Due to the significant impact of the pandemic on mental health need, we strongly advise that the DoH repeat the prevalence survey in 2023.
1.8 | The Department of Health (DoH) should review the implementation of the Regional Referral Criteria for Step 2 and 3 CAMHS to: a) Develop a comprehensive training and awareness raising programme, to ensure that all ‘referral agents’ are aware of the referral process and their role within it | 2 (a) | On an annual basis Trusts, along with HSCB will reflect back on referral trends to identify changes in referrals patterns and undertake specific awareness rising activities as required. | Rolling Annually - to be completed by June of each year with engagement activity therefater | HSBC | HSCT/Referring agents | In progress | Covid has impacted this work. Trusts have delivered training to GPs and each have specific arrangements in place to support the referrals processes including delivery of Webinars, delivery of dedicated programme and in SHSCT, the appointment of a dedicated referral co-ordinator to support the referral process and address issues as they arise. | The work to raise awareness and review referral processes from GP to CAMHS is welcome. We would encourage further discussion about how awareness raising programmes could be established for the full range of referral agents, to ensure alternative pathways to CAMHS are being fully utilised. Thereby, taking pressure of GPs and ensuring those most knowledgable about a child's needs are enabled to make a referral.
Objective: Joined up working between services
1.9 | Full implementation of the Managed Care Network (MCN) as a matter of urgency, and review of its potential as a mechanism for co-ordinating and operationalising a whole system approach to the delivery of human rights compliant mental health services for children and young people. | 1 (e) | Establishement of a fully implemented and operational Managed Care Network (MCN) | 2022-01-30 | HSBC | DoH | In progress | Recurrent funding has been secured for the Managed Care Network and HSCB are finalising plans for implementation. Recruitment of the MCN clinic director is underway. | The process to recruit staff to establish a managed care network has taken an inordinate amount of time, particularly as it has always been viewed as a priority action.
1.1 | Introduce multi-disciplinary and multiagency decision making processes in individual care planning, to ensure that support pathways for young people are direct and effective. | 2 (c) | Develop MH Liaison Service (for 16+), CAIT and acute care pathways for children and for young people. | This action will be taken forward as part of the Mental Health Strategy 2021-2031 | DoH | DoH | In progress | This action is being taken forward as part of the 2021-31 Mental Health Strategy. Action 27 of the Strategy is to "Create a Regional Mental Health Crisis Service that is fully integrated in mental health services and which will provide help and support for persons in mental health or suicidal crisis". A new regional crisis service was announced in August 2021 and a implementation plan for the new service has been developed by the HSCB/PHA and provided to the Department on 19 November 2021. Action 6 of the "Regional Mental Health Crisis Service for N Ireland" is to "deliver a regionally consistent mental health liaison service across all Emergency Departments and accute hospital settings , so that all who require a mental health assessment, regardless of age, will receive such assessment at the time of need". | In Still Waiting NICCY made a number of specific recommendations on Emergency Departments- It recommended the implementation of RCPCH Standards, associated RQIA inspection process to monitor compliance with these standards, and the regional roll-out of a clinical decision making unit (recommendations 21, 22,24). NICCY also fed these recommendations through the specific consultation process for crisis services- without further information on the new service we can't assess if progress made aligns with NICCY recommendations.
1.11 | Develop regional protocols which allow a broader range of VCS organisations working with young people with mental health problems, to make a direct referral to Step 3 CAMHS or with the support of a GP (fast track process via GP) | 2 (b) | Self Harm Intervention Programme (SHIP) referral pathway for children and young people to be kept under review. | Ongoing | DoH |  | In progress | An evaluation of the service has commenced by the PHA. However, this has been delayed due to pandemic response. | The SHIP programme is a good example of where referral pathways could be simplified and used to trial a system that enables specialist VCS organisations to refer directly to other specialist services. If effective, NICCY would like to see protocols developed with a wider range of VCS that are working closely with children and young people with mental health problems.
2. Key Theme: Accessing Help
Ref ID | Recommendation |  | Action | Completion Date | Lead | Key Partners | Status | Comments
Objective: Removing barriers that stop young people accessing services
2.1 | Introduce a dedicated telephone advice line for statutory CAMHS, which professionals, parents/carers and young people could use as a way of improving the communication and support offered by services, whilst young people are waiting for an appointment or between appointments. | 10 | Scope what supports are currently on offer for Children and Young people awaiting appointments or in between appointments. Analyse any resource and practical implications for implementing this. | 2022-03-30 | HSCB/HSCT | DoH | In progress | To be taken forward by HSCB and HSCT's. | Progress on this recommendation is important, and it is recognised that the need for improved accessiblity and communication between patients and health professionals is a challegne across the HSC system, not only mental health, as outlined in NICCYs recent review of child health Waiting Lists- More Than A Number.
2.2 | Introduce a Mental Health Passport Scheme that contains key information on young people, which they want professionals involved in their care to be able to access. | 9 | Consider creation of a Mental Health Passport Scheme, through existing portals. | This action will be taken forward as part of the Mental Health Strategy 2021-2031 | DoH | DoH | In progress | This action is being taken forward as part of the 2021-31 Mental Health Strategy. Action 11 of the Strategy is to "Ensure that the needs of infants are met in mental health services, and meet the needs of vulnerable children and young people when developing and improving CAMHS, putting in place a ‘no wrong door’ approach". | Good to see this action being embedded into the Mental Health Strategy- further information required on plans and exact time frames.
2.3 | Develop a children and young people specific Regional Integrated Elective Access Protocol (IEAP). | 11 | Review Integrated Elective Access Protocol (IEAP) to ensure fit for purpose for children and young people. | 2021-12-31 | DoH | HSCB | complete | A review of the Integrated Elective Access Protocol was completed by HSCB in 2020 and was endorsed by DoH in November 2021. A further review of the IEAP is expected to take place in 2022. Both the Acute care and the Mental Health services IEAP include provision for children and young people. | NICCY welcomes that a review of the IEAP has been conducted. We seek further information on the process undertaken to assess the effectiveness and compliance with the IEAP and if children, young people and their parents / carers were consulted as part of the review.
2.4 | An evaluation of the compliance with, and effectiveness of, the Card Before You Leave scheme (CBYL) for children and young people in A&E should be carried out. | 25 | Review the Card Before You Leave (CBYL) Scheme for children and young people. | 2022-03-31 | HSCB | DoH | In progress | To be taken forward by HSCB. | Need system wide process for ensuring CYP presenting to ED during a mental health crisis are supported to access all appropriate services- the response must comply with RCPCH Standards-‘Minimum Care Standards for Children and Young People in Emergency Care Settings who Present with Mental Health Problems’ (RCPCH, 2018). See response to 1.10 also.
Objective: Greater Flexibility and choice in how young people engage with services
2.5 | Introduce a dedicated telephone advice line for statutory CAMHS, which professionals, parents/carers and young people could use as a way of improving the communication and support offered by services, whilst young people are waiting for an appointment or between appointments. | 10 | Develop an APP that will assist young people requiring help and support with health and social wellbeng or who may have difficulty in engaging with CAMHS | 31 June 2021 | HSCB | DoH | Complete | HSCNI in partnership with ORCHA (Organisation for review of care and health apps) developed a library of high quality, convenient Apps to support the health and wellbeing of the population. | We welcome this intitiative. It is important that the effectiveness of these APPs are evaluated for different demographic groups. It is only when the action achieves the intended outcome that this action can be deemed complete i.e. young people report improved commmunication and improvement in levels of support.
2.6 | Review appointment systems and consider the introduction of: a) An online booking system so young people and carers have more control over the appointment time given; b) Appointment slots available outside of school hours; c) The option of appointments being held in their own home or close to home; d) Reminder texts about appointments; and e) The option of making remote contact with a trained mental health counsellor between appointments i.e. telephone text. | 8 (a-e) | Review CAMHS appointment systems in relation to recommendation 8 to consider the viability and practical implications. | 2022-03-31 | CAMHS HoS | DoH | In progress | Social distancing restrictions as a result of the pandemic have resulted in an increased use of video and tele conferencing facilities for appointments, where clinically appropriate and suitable to do so. This has meant more choice and flexibility for the patient in terms of appointment times and reduced travel. This is being kept under review but early indications are that it is working well and has been well received. However, this format is not appropriate for all and some patients prefer to have face to face contact which is accommodated, with social distancing and infection prevention control measures in place. Generally an online booking system cannot be facilitated because of Trust IT systems. | The pandemic has been the cataylst for the HSC introducing more technology into its day to day work with patients, this is welcomed but also needs to be closely evaluated to understand the circumstances under which this works for children and young people. In relation to the challenges of establishing an online booking system- whilist we recognise the challgenges of embedding technology into the current system, it is our understanding that ENCOMPASS will suppport an information management system that should allow for modern ways of communicating with patients that improves efficency and reduces maladministration and administrative burden on staff. The need for improved information management systems was an issue raised in NICCYs recent Review of the Child Healthcare system more generally (More Than A Number).
2.7 |  |  | Fully implement CAMHS care pathway across NI, including gap analysis and where additional resources should be deployed. |  | MCN | Gavin Quinn DoH | Complete | CAMHS care pathway is fully implemented. A review of resource is ongoing as part of business as usual. Where additional resources are needed this would be considered by HSCB and DoH. | The CAMHS Care Pathyway document is complete. However, implementation of the CAMHS Pathway is a significant undertaking as it involves translating policy into practice. The gap analysis process to identify where services are not in place will be very important and will inform any fund mapping exercise (see also 1.3). This action will not be complete until the the full range of services that form the care pathways are in place.
3. Key Theme: Supporting adults working with children and young people
Ref ID |  |  | Action | Completion Date | Lead | Key Partners | Status | Comments
Objective: Mental health training for all professionals who work with young people
3.1 | Introduce a mandatory programme of mental health training for all professionals likely to come into contact with young people with mental health problems, this must include GPs. The training needs to develop core professional competencies to respond to young people in a sensitive, competent and age appropriate way. | 5 | Roll out at Trust level of short course programme on the CAMHS Care pathway to GPs and other children services. | Completed in March 2020 | HSBC |  | Complete | Short Course Programme completed and disseminated to Trusts. HSCB will review impact of this with HSCT Heads of Service for CAMHS. | We welcome the initial roll out of this initiative across GP surgeries and other childrens services but seek assurances that it has been provided to all referral agent groups outlined in the CAMHS Pathway document. These are GP, Child and Family Social Services, Paediatric Services, Child Health Services, Education Welfare Services including the Independent Counselling Service for Schools (ICSS), voluntary agencies within the Stepped Care Model and Family Support Hubs (see also 1.8). We seek further information on the plans to make this a rolling training programme for referral agent groups.
Objective: Integrated working across the system to strengthen children and young people’s emotional and mental wellbeing
3.2 | Designated mental health practitioners, trained to work with young people, should be attached to every GP surgery. | 6 | Implement primary care Multi Disciplinary Teams with a mental health practitioner attached to all GPs across the region, with specific training on working with young people. | Phased approach in line with agreed road map (Full Implementation over the next 6 years) | DoH | HSCB, GP Federation, Workforce training | In progress | The MDT model is currently in place or in development in 5 of the 17 GP Federation areas – Down, Derry, West Belfast, Causeway and Newry & District with a small footprint introduced in North Down and Ards late in 2020/21. There are currently 56.9 wte mental health practitioners (MHPs), supported by 5 mental health managers, within the current Primary Care Multi-Disciplinary Teams footprint. These MHPs work with patients of all ages to ensure they have access to timely assessment and appropriate support to address their individual mental health needs. . | The progress made to maintain /develop MDTs in the current circumstances must be acknowledged. However, it is important that the number of children reached, benefits experienced, outcomes achieved etc. is part of the monitoring and review of this model.
3.3 | Statutory mental health professionals should also be available to every primary and post primary school in Northern Ireland. | 6 | Establishment and launch of additional specialist mental health support available for schools, delivered through the Emotional Health and Wellbeing Education Framework: - Text a Nurse (Post primary) - Expanded rise provision (Primary) - CAMHS school service (Primary and Post Primary). - Extension of Abbey School Nursing pilot. | 2022-01-31 | DE | HSCB, PHA and Schools | In progress | Text a Nurse was launched in February 2021,the remaining initiatives launched in September 2021. CAMHS school service is anticipated to commence in 2022. | NICCY welcomes all the new programmes / initiatives coming from the Emotional Health and Wellbeing in Education Framework. The annual recurrent funding of £6.5 million will make programmes sustainable in the long-term which is extremely positive. We are keen to see the mental health link person attached to every post primary school established and the full roll out of the primary school counselling service- we recognise that resource to progress this work at departmental policy level is stretched and that considerable effort is being made to ensure this happens as soon as possible.
4. Key Theme: Specialist Support
Ref ID |  |  | Action | Completion Date | Lead | Key Partners | Status | Comments
Objective: Greater range of community based mental health support
4.1 | A range of community based after care supports must be available to young people discharged from Community CAMHS or inpatient care. | 12 | Provide greater opportunities for mental health support community and voluntary sector organisations to apply for funding from the Department of Health's core grant funding scheme, through introducing an open call for applications to the scheme. | 2022-04-01 | DoH | Project Board | In progress | The £10m Mental Health Support Fund was announced on 19 April 2021 and was open to community and voluntary sector organisations with charitable purposes offering services for people with mental ill health throughout Northern Ireland. It is also intended that C&V sector organisations will have an opportunity to apply in the coming months for DoH Core Grant Funding from April 2022. | We welcome the funding to the VCS and understand this to be one off funding to address COVID specfic pressures. As set out in action 1.4, longer term sustainable funding to the VCS is essential to strengthen the partnership in which both statutory and VCS are formally recognised and resourced as a critcal part of the mental healthcare system. The new 3 yr budget cycle and the evidence during covid of the role of the VCS should make this more achievable and desirable than it has ever been.
4.2 | Provide resources to GPs to allow them access to a greater range of self-help supports to offer young people. | 13 | Provide a greater range of self-help support for young people. | 2022-01-31 | HSCB | HSCT | In progress | HSCB will link with colleagues in MDT's to ensure the Youth Wellness Hub and directories of services that provide help to young people are shared. | It makes sense for MDTs to promote self-help supports with CYP as part of their engagement. We welcome this work and will follow progress as part of the wider MDT roll-out.
Objective: Needs led support and treatment in mental health hospitals
4.3 | The administration of prescription medication for young people must comply with NICE guidelines. Where medication is prescribed to a young person with a history of alcohol and/ or drug problems this should be risk assessed and appropriately supervised. HSCB must monitor prescribing data to ensure compliance with NICE guidelines. | 14 | Undertake a review of prescribing data and ensure medication for mental health to children and young people is appropriate. | 2021-04-01 | HSCB | DoH | Complete | A study to test a prescribing sample "Prescribing in Child and Adolescent Mental Health Services" was carried out by NHSCT in July 2020. | NICCY welcomes the review of prescribing data in the NHSCT ensure the administration of medication to children and young people for mental health is appropriate. We require further info on whether consideration is being given to a similar exercise across other HSCTs, and seek an update on actions being taken to bring administration rates down, including in cohorts where prescribing is disproportionately high. NICCY CAMHS Data Report 2014-2021 shows that between 2018-2020 the number of prescriptions administered to under 18’s has increased, this includes under 12's and inlcudes the administration of drugs not recommended by NICE. It is vital that the availability of psychological therapies improves which should bring these rates down. It is impossible to meet NICE Guidelines without adequate access to alternatives to medication which is not currently the case in NI.
4.4 | The complete range of evidence based, effective psychological treatments and alternative therapies should be made available to children and young people. Targets for accessing such treatments should be set in the best interests of children and young people, met, closely monitored and reviewed. | 15 | Fully implement psychological therapies in CAMHS, as per the existing 2010 Psychological Therapies Strategy. | This action will be taken forward as part of the Mental Health Strategy 2021-2031 | DoH | DoH | In progress | This action is being taken forward as part of the 2021-31 Mental Health Strategy. Action 19 of the Strategy is to embed psychological services into mainstream mental health services and ensure psychological therapies are available across all steps of care. | We agree that the Psychological Therapies Strategy should be updated to reflect current levels of need and kept in line with NICE guidelines. We fully agree that psychological therapies should be part of CAMHS, we also recommend that waiting time figures for all available psychological therapies for CYP are monitored and published as part of the CAMHS dataset. We require further information on timeframes for developing psychological therapies and filling gaps in workforce. It is vital that the mental health workforce planning review recommends clear actions to address this issue.
4.5 | Children should receive the most appropriate and effective inpatient care for their mental health. This should be tailored and appropriate to the level of need, and include the provision of inpatient intensive care where necessary. | 18 | Evaluate and analyse the need for Psychiatric Intensive Care provisions in Northern Ireland and make decision on the future need. | 2021-02-01 | HSCB |  | Complete | 4 PICU beds available from 1st February 2021. | We understand that an analyse of the need for PICU beds was conducted which led to the introduction of 4 extra beds at Beechcroft. In Still Waiting, rec 20 referred to the use of Extra Contractual Referrals and asked for a review of young people referred outside of NI for mental health treatment. We understand that a review of ECRs has been conducted and we require clarity on how this review will inform child inpatient mental health service planning to reduce the use of ECRs.
4.6 | Reasons for the increase in the number of young people being detained in Beechcroft need to be urgently interrogated. Similarly, an examination of the variances in referral rates to Beechcroft by HSCTs should be carried out. A clear policy response and actions should be taken forward as a result, in the best interests of children and young people. | 19 | Evaluate and analyse the use of detentions in Beechcroft. | From January 2021 onwards - data to be analysed every 3 months. | HSCB |  | Complete | A report with 3 years data is now available. This will report will be completed every 6 months. | We welcome the establishment of a monitoring system to review use of detention in beechcroft. It would be useful to better understand the review process for these reports- who involved in analysing data and considering response.
Objective: Children and Young People on Adult wards
4.7 | The practice of admitting children onto adult mental health wards should end. Children and young people requiring inpatient mental healthcare should receive it separately from adults. | 17 | Ensure suitable protocols exist for children who are admitted to adult wards | Complete | DoH |  | Complete | All Health and Social Care Trusts have a protocol in place to manage admissions of children under the age of 18 to adult wards. Where appropriate, the relevant provisions of the MCA provide a statutory requirement to ensure age appropriate accommodation is avaible. | The Committee on the Rights of the Child is categorical in its position that a child should never be admitted to an adult mental health ward. Comprehensive mental health care for children should be in place to meet need so that such situations do not arise. Whilst we recognise the intention behind the development of a protocol, this should not be required and it is impossible to provide child rights based healthcare for children in an adult mental health facility / environment. We also continue to be unclear about the extent of the oversight role RQIA has in each individual circumstance where a child is admitted to an adult ward.
4.8 | When a young person is admitted to a general paediatric bed for mental health treatment or care, the DoH should request that RQIA are notified, and provided with information on what care and treatment is being provided. When a young person is admitted to a general paediatric bed for mental health treatment or care, the DoH should request that RQIA are notified, and provided with information on what care and treatment is being provided. | 50 | Review processes and consider a regional protocol for notifying RQIA when children are admitted to any adult wards for treatment or care. | 2022-04-01 | DoH | HSCB | In progress | To be taken forward by DoH | Work to address this action does not appear to have started. It is important that a clear timeframe is set for this. |  | Action 53 should say paediatirc
Objective: Implement and monitor minimum care standards in A&E
4.9 | Crisis intervention support for children and young people should be available 24 hours a day, all year round, in all HSCTs. | 23 | Create a regional crisis service for children and young people. | This action will be taken forward as part of the Mental Health Strategy 2021-2031 | DoH | DoH | In progress | This action is being taken forward as part of the 2021-31 Mental Health Strategy. Action 12 of the Strategy is to "Create clear and regionally consistent urgent, emergency and crisis services for children and young people that will work together with crisis services for adult mental health" and Action 27 is to "Create a Regional Mental Health Crisis Service that is fully integrated in mental health services and which will provide help and support for persons in mental health or suicidal crisis". A new regional crisis service was announced in August 2021 and an implementation plan for the new service has been developed by the HSCB/PHA and provided to the Department . Action 6 of the "Regional Mental Health Crisis Service for N Ireland" is to "deliver a regionally consistent mental health liaison service across all Emergency Departments and accute hospital settings,so that all who require a mental health assessment, regardless of age,will receive such assessment at the time of need". | We welcome the linkages made between the MHS and this SWAP action. It is important that the new regional mental health crisis service addresses the issues raised by childen and young people in the Still Waiting Review. (Also see response to 1.9-1.11.)
5. Key Theme: - Moving from child to adult services
Ref ID |  |  | Action | Completion Date | Lead | Key Partners | Status | Comments
Objective: Transition planning from CAMHS to post-18
5.1 | A Regional Transitions Policy and Procedure which is compliant with NICE Transition Guidelines should be developed and implemented, to ensure that all young people transition smoothly between CAMHS and AMHS. Develop a mental health ‘bridging service’ for young people aged 16 to 25 years old, that allows for a smoother, flexible and young person centred transition between services. | 29 | Develop proposals for transitions between CAMHS and adult mental health services, engaging widely with all relevant stakeholders | This action will be taken forward as part of the Mental Health Strategy 2021-2031 | DoH | DoH | In progress | This is being taken forward as part of the 2021-31 Mental Health Strategy. Action 13 of the Strategy is to "Develop proposals for transitions between CAMHS and adult mental health services, engaging widely with all relevant stakeholders". | In last years update we were informed that a task and finish group with service users had considered how transitions could be improved. NICCY also was part of an exercise in which a number of proposals were discussed. It is unclear what further evidence needs to be collected for reform work to begin. The planned transition and after-care support for those who do not transition to AMHS must also be fully considered within the new service models.
5.2 | As above | 29 | Develop a transition dataset as part of the CAMHS dataset. | TBC | HSBC | DoH | Complete | This is contained within CAMHS dataset. See action 1.5 | It is positive that info on yp transitioning to AMHS is being collected on a standardised and regional basis through the CAMHS Dataset. We reitetate the overarching need for CAMHS Activity data to be published and available to public data users.
6. Key Theme: - Flexible treatment options | [9 empty] | i
Ref ID |  |  | Action | Completion Date | Lead | Key Partners | Status | Comments
Objective: Provide clear information on service standards and how to make a complaint and feedback
6.1 | Develop user-friendly guidance for young people and parents/carers which explain their right to complain, and sets out the minimum standards of care they should expect. | 28 | Audit of existing complaints process across Trust and review complaints made within 2 years for baseline. Consult with existing Service User groups re: appropriateness of current arrangements. | 2022-03-31 | HSBC | Trusts/YP/Carers | In progress | Young people involved in CYPSP and the Youth Wellness Hub are considering this action. | PCC may also be able to support this work. Clear service standards are a pre-requiste part of a transparent and accountable complaints / feedback system.
Objective: Strengthen involvement of young people in decisions about their care and how services are delivered
6.2 | Development of an action plan to strengthen advocacy, enhance peer support, and develop practice standards to evidence the involvement of young people in service development, and in their own care planning. Revise and establish fora in each HSCT to support the active engagement of children young people and their parents/carers, to inform both acute and community care. Views expressed through this engagement should be considered at the practice based meetings, where day to day issues are raised and discussed. | 26, 27 | Scope children and young people involvement in service evaluation and development. Consider development of an action plan and setting up a mental health youth forum in each Trust to support this action. | 2022-03-31 | HSBC | Existing YP forums/ | In progress | HSCB will carry out a scoping exercise across Trusts to identify and review existing arrangments and determine best way forward. | It is important that this work is progressed and fully recognised as an essential component of service delivery as it provides asssurances that services are meeting standards, needs and achieving outcomes important to children and young people. Equity of access to independent advocacy must be included as part of this review work- this includes mapping out existing services available to children in inpatient care, new provisions as set out in MCA for 16+ yr olds / provisons for under 16's under an amended MHO and identifying gaps in access to services and the overall scope of support offered.
Objective: Ensure full range of evidence based treatment interventions are available in line with NICE Guidelines
7. Key Theme: - Mental health awareness and understanding
Ref ID |  |  | Action | Completion Date | Lead | Key Partners | Status | Comments
Objective: Educate children and young people about their emotional wellbeing as part of the curriculum
7.1 | Comprehensive mental health and wellbeing education for pupils should be provided as a core part of the education curriculum. This should ensure that all young people have sufficient vocabulary to talk about their emotional well-being and mental health, know how to look after their mental health, have an understanding of the help available and how to access it. | 32 | Promotion, prevention and early intervention around emotional wellbeing will be at the core of The Emotional Health and Wellbeing Framework (the Wellbeing Framework) being developed jointly by DE, PHA, DoH and the Education Authority. This will include use of the curriculum and curriculum based resources available to support teachers in its delivery. | This action will be taken forward as part of the Emotional Health & Wellbeing in Education Framework | DE |  | In progress | This will be taken forward as part of the Emotional Health & Wellbeing in Education Framework and Implementation Plan which was published on 26th February. | CYP involvement essential as part of this process. CYP have been consistent in saying that current PSHE / LLW MH & Wellbeing modules are poor.
Objective: Education providers should work more closely with mental health services
7.2 | Education and mental health service providers should develop formal partnerships in order to holistically meet the needs of children in education at all levels, and for those children and young people receiving their education ‘other than at school’. | 33 | Education and Health interventions delivered under the Emotional Health & Wellbeing in Education Framework to be delivered as part of an integrated model of support across Education and Health & Social Care services to address the emotional health & wellbeing needs of children & young people within educational settings. | This action will be taken forward as part of the Emotional Health & Wellbeing in Education Framework | DE |  | In progress | This will be taken forward as part of the Emotional Health & Wellbeing in Education Framework and Implementation Plan which was published on 26th February. | NICCY welcomes the range of initiatives / programmes coming out of the EHW in Education Framework that meets this objective. We will follow the roll- out of the Emotional Wellbeing Teams in post primary which will include a CAMHS Link Worker and the primary school counselling / therapies pilot with particular interest. We are also very interested in how the framework is embeded into special schools and EOTAS to include adaptations made to programmes to meet unmet needs / supports.
Objective: Provide information at key stages and transition points
7.3 | Equal emphasis should be placed on the measurement and improvement of the well-being of children and young people in education, as on academic attainment. Schools should be inspected by ETI on their ability to develop the conditions required to nurture young people’s wellbeing. | 34 | The Emotional Health and Wellbeing in Education Framework will provide clear structures of support, including clarification of the links and pathways of referrals to the appropriate services, based on the child/young person’s needs. | 2022-01-31 | DE |  | In progress | In publishing the Emotional Health and Wellbeing in Education Framework, the Department of Education has highlighted the importance of the wellbeing of our children & young people and the implementation combine to form an integrated model of support across Education and Health & Social Care services to effectively support them in their educational setting. ETI has also incorporated consideration of wellbeing within the inspection process. | It is noted that ETI are considering incorporating wellbeing into their inspection process. To progress this work a mechansim for measuring wellbeing in the form of an annual pupil survey is required. The PISA survey offers a good baseline for this work to be progressed and dovetails with outcome measurements required for the CYP Strategy, Mental Health Strategy and the evaluation of the EHW in Education Framework.
Objective: Strengthen public awareness and community capacity building
7.4 | A programme of public awareness and community capacity building on mental health and emotional well-being should be developed, and regionally implemented with a specific focus on geographical areas, and groups with the highest risk factors for poor mental health. | 36 | Commission qualitative research on mental health literacy, language and awareness of services appropriate for children and young people to inform future awareness raising programmes including for example the Change Your Mind programme which is designed to tackle mental health stigma and discrimination. Subject to resource availability, pilot two programmes in 2020/21 to support resilience in post-primary schools; and embed Mental and Emotional Wellbeing in the curriculum to maximise success in further and higher education. Links with Protect Life 2 objective and associated actions to improve awareness of suicide prevention and associated services. | Through 2020/21 | DoH |  | Complete | Stress Control in Schools Programme was piloted in 9 post-primary schools in North Belfast, throughout 2019/20. Aimed at 15 year olds, it incorporates CBT, mindfulness and positive psychology; and is run over 8 weekly single school periods, delivered by teachers who can be trained in one day. 59 teachers were trained and the programme was partially delivered to 1200 pupils. Challenges were experienced in delivering the programme in already busy school timetables. Independent evaluation of the BLOOM programme has recently been completed. | We welcome the pilot work conducted through 2020/ 21 and the evaluation work that accompanied it. We are unclear about the sustainablity of programmes which is required to ensure this objective remains a focus. We also see links with this action and 7.1 to improve and develop curriculum and curriculum based resources available to support teachers in its delivery.
8. Key Theme: - Young people with additional needs
Ref ID |  |  | Action | Completion Date | Lead | Key Partners | Status | Comments
Objective: Equal access for young people with a learning disability to services and support
8.1 | A comprehensive and integrated mental health service model across Northern Ireland for children and young people with a learning disability should be agreed and implemented. This model must ensure that young people with a learning disability can access comparable services and support as young people without a disability. | 39 | Understand current provision of ID CAMHS across all Trusts through undertaking scoping exercise of existing pathways. | 2022-03-31 | HSCB | DoH | In progress | HSCB will progress work in this area however, this action can also be taken forward as part of the 2021-31 Mental Health Strategy. Action 11 of the Strategy is to "Ensure that the needs of infants are met in mental health services, and meet the needs of vulnerable children and young people when developing and improving CAMHS, putting in place a ‘no wrong door’ approach". | The Mental Health Strategy is an important vehicle for acheiving this action as it makes a commitment to ensuring that every child gets access to adequate mental health support that meets their needs. It also acknowledges that children with additional needs such as learning disablity experience greater barriers to accessing support and this must be addressed. The lack of regional consistency in service provison is well known, however, to inform service planning we welcome an updated rapid review of HSCT services and pathways and would recommend that part of the focus of this exercise includes an assessment of whether and to what extent HSCT services are in line with the CAMHS STEP Care model - in particular Step 3 CAMHS.
8.2 | Immediate steps must be taken to ensure that all detentions of children and young people in the Iveagh Centre under the Mental Health (Northern Ireland) Order 1986 is proportionate and appropriate. | 40 | Establish a regional Board with HSCB/Iveagh and 5 Trusts to strengthen operating procedures within Iveagh to prevent delayed discharges as well as keep focus of plans to discharge. | 2021-05-01 | HSBC | Iveagh/HSCB/Trusts | Complete | Structures established to oversee delayed discharges. | NICCY welcomes the introduction of any new strutures that prevent delayed discharge and improve disharge planning. Before closing this action, it is important these new structures are evaluated to ensure they meet the intended outcome.
8.3 | A comprehensive and integrated mental health service model across Northern Ireland for children and young people with a learning disability should be agreed and implemented. This model must ensure that young people with a learning disability can access comparable services and support as young people without a disability. | 39 | Development of the Children and Young People Emotional Health and Wellbeing Framework including scoping of a regional ADHD service. | 2022-03-31 | HSBC |  | In progress | This will be taken forward as part of HSCB Children and Young People Emotional Health and Wellbeing Framework/Review of children's Disability Framework. | See 8.1 & 8.4
8.4 | A comprehensive review of community based emotional, mental and behavioural support services for young people with a learning disability. |  | Carry out a review of community based emotional, mental and behavioural support services for children and young people. | 2022-04-01 | HSBC |  | In progress | This will be taken forward as part of HSCB Children and Young People Emotional Health and Wellbeing Framework/Review of children's Disability Framework. | Whilst we recognise that the frameworks referenced focus on the needs and access to support for children with a disability / neurodevelopmental needs. It is important that the focus of this action remains on the provision of community mental services. Having such key services in place is a pre-requistie for pathway plans / frameworks as they become irreelvant without services.
Objective: Access to services to address mental health and substance use problems at the same time
8.5 | Inpatient care and treatment should be provided for young people with co-occurring drug and/or alcohol and mental health problems, who cannot be safely and effectively supported within the community. This provision should take a holistic approach to need, provide a range of interventions and be fully integrated into the Stepped Care CAMHS service model. | 44 | Establish a service that will provide support and care for young people with co-occuring drug and/or alcohol and mental health problems. | This action will be taken forward as part of the Mental Health Strategy 2021-2031 | DoH | DoH, DoH | In progress | This action is being taken forward as part of the 2021-31 Mental Health Strategy. Action 28 of the Strategy is to "Create a managed care network with experts in dual diagnosis, supporting and building capacity in both mental health and substance use services, to ensure that these services meet the full needs of those with co-occurring issues ". | It is vital that mechansims are put in place to ensure that there will be sufficent focus on children in these planning groups and that services for children are prioritied as critical to life long prevention, early intervention and minimising harm.
8.6 | Statutory CAMHS should adopt a ‘harm reduction approach’ to ensure that young people can access mental health support whilst withdrawing from substances. Appropriate levels of supervision and support for young people withdrawing from substances should be provided. Universal and timely access to Drug and Mental Health Services (DAMHS) should be available across Northern Ireland. DAMHS should be closely aligned to CAMHS, and closely linked to Step 2 commissioned drugs and alcohol services. Step 4 specialist intensive community based support and interventions for young people with drug and/or alcohol and mental health problems should be expediently developed, and provided across Northern Ireland. This should include day treatment programmes and age-appropriate interventions. Inpatient care and treatment should be provided for young people with co-occurring drug and/or alcohol and mental health problems, who cannot be safely and effectively supported within the community. This provision should take a holistic approach to need, provide a range of interventions and be fully integrated into the Stepped Care CAMHS service model. | 41, 42, 43 | The HSCB and the PHA will review services available for children and young people, particularly looking at the transition of young people from children to adult services, and ensure this is incorporated into the new outcomes-focused strategic plan being developed to replace the Alcohol and Drugs Services Commissioning Framework. | 2022-12-30 | DoH | PHA/HSCB | In progress | This work will be taken forward as part of the the Substance Use Strategy 2021-2031 which was published by DoH on 7 September 2021. The necessary implementation bodies for the new strategy are in the process of being established, with the overarching Programme Board chaired by the Chief Medical Officer holding its first meeting on 30 November 2021. In addition the HSC Substance Misuse Strategic Planning Group jointly chaired by the PHA and HSCB has also been established and held its first meeting on 23 November 2021. | As stated above it is vital that mechansims are established to ensure that there is sufficent focus on children in the planning, resourcing and implemention of the substance misuse strategy. Direct engagement with young people and the organisations that support them is essential at all stages going forward.

## Decision Log
Decision Log
Note: This log captures all decisions that have been made during this project.
Updated:
Ref ID | Date Logged | Details of the Decision Made | Decision Made by | Date Decision Made | Next Steps
1
2

## Issue Log
Issue Log
Note: This log captures all decisions that have been made during this project.
Updated:
Ref ID | Date Logged | Details of the Issue | Next Steps | Completion Date | Status | Comment